## Slide 1
EDPRS 3 elaboration process
MINECOFIN
26th May 2017

## Slide 2: Outline
Background
EDPRS 2 Overall performance
Rationale for elaboration of EDPRS3
Inclusiveness strategy for EDPRS 3 elaboration
Participatory Planning – DDS Elaboration
EDPRS 3 elaboration Coordination Framework
EDPRS 3 Accomplished Milestones/ roadmap

## Slide 3: Background
The EDPRS 2 was adopted by the Cabinet in May 2013 and its lifetime spans up to June 2018 - Now almost in the last year of its implementation.
The overall objective is to accelerate progress to middle income status
Interventions to enable achievement of desired progress are enshrined in the four thematic areas (Economic Transformation, Rural Development, Productivity and Youth Employment and Accountable Governance) as well as the selected Foundational Issues and Cross-cutting Issues.
Indicators in the EDPRS 2 Monitored from the Sector Frameworks in consultation with sector working groups on an annual basis.
EDPRS 2 mid-term evaluation is also in the finalization phase to inform EDPRS 3 elaboration.

## Slide 4: EDPRS 2 Overall performance
Out of the 30 core EDPRS 2 indicators, 27 were evaluated, 5 (19 %) were achieved, 7 (26%) are on-track, 11(41 %) are on-watch and 4 (15%) are off-track
Chart: 
| Achieved | On-Track | On-Watch | Off-Track
Overall Achievement | 0.18519 | 0.2963 | 0.37037 | 0.14815
Key citizen participation & inclusiveness achievement:
Citizen’s were involved at all level through different framework (UMUGANDA, etc..)

## Slide 5: Performance by Thematic Area
Chart: 
| ECONOMIC TRANSFORMATION | RURAL DEVELOPMENT | PRODUCTIVITY AND YOUTH EMPLOYMENT | ACCOUNTABLE GOVERNANCE | FOUNDATIONAL AND CROSSCUTTING ISSUES
Achieved | 5
On-Track | 4 | 2 | 1 | 1
On-Watch | 1 | 4 | 2 | 2 | 1
Off-Track | 2 | 1 | 1

## Slide 6
EDPRS 3 elaboration

## Slide 7: Rationale for elaboration of EDPRS3
EDPRS 2 and related strategies (SSPs and DDPs) to be completed in June 2018
Important regional and global commitments to be integrated in long and medium term plans:
  SDGs
  EAC Vision 2050
  Africa Agenda 2063

## Slide 8: Inclusiveness strategy for EDPRS 3 elaboration
A mass Communication campaign to ensure;
  Stakeholder consultations and outreach for the EDPRS 3 to ensure that as much as possible, no one is left behind in consultations, through;
    Multiple and widespread communication channels e.g. toll free sms line (2018 for EDPRS 2), TV and Radio spots, Kubaza bitera kumenya, Community radios ( Radiyo z’Abaturage ), social media (Twitter, etc..)
    Grassroots outreach platforms (Inteko Z’Abaturage, Umuganda)
  Consultations with multiple stakeholders will aim at promoting ownership of the National Strategies.
  Engagement trough participatory planning

## Slide 9: Inclusiveness strategy for EDPRS 3 elaboration (Cont’d)
Targeted audience/ groups for consultations:
  All National stakeholders that range from Citizens,
  Policy Makers (Executive, Parliament, and Judiciary), Political parties, Public Servants,
  Civil Society, Private Sector, Development Partners,
  Youth, Women, the elderly, People living with disabilities
  Academia and research institutions
  Rwandans living in Diaspora, friends of Rwanda among others.

## Slide 10: Participatory Planning – DDS Elaboration
General Process Design
STEP 1
Identifying citizens’ needs
STEP 2
First Draft of DDS by aligning the inputs (citizens needs, LED strategies, sector strategies, national targets…)
STEP 3
Public Hearing of the DDS Draft
STEP 4
Finalizing the DDS by taken into account the results of the public hearings
STEP 5
Public Information of the final DDS
STEP 6
Monitoring of the DDP/ Midterm Evaluation - Revision of the DDS
STEP 5 a
Feedback of the statements –Report on the Public Hearing

## Slide 11
Citizens’ need assessment and public hiring procedure:
District administration informs the public on why and when the participatory needs assessment will take place- through campaigns
Meeting will be organized at Cell level
Village people identify and prioritize their needs in separate village-wide brainstorming processes using a defined Ranking Methodology
All cell-wide Priority-List (approved by the Cell Council) is submitted to the Sector Council for prioritization.
Approved priorities and draft DDP to be presented to the public through public hiring.
    to discuss the DDS draft with district and sector staff and ask questions
    to give their statements on the DDP draft: written or orally – the orally given statements are to be noted by the district or sector staff;
    all statements are collected in a so called “ideas-mailbox”.
Participatory Planning – DDS Elaboration

## Slide 12: Vision 2050, EDPRS 3 elaboration Coordination Framework
Policy Guidance and approval | Cabinet |  | 
Oversight | National steering committee |  | 
Overall Coordination | MINECOFIN |  | 
Local government coordination | MINALOC |  | 
Technical consultation forums | Technical Steering Committee (PSs and DPs) |  | 
 | Thematic Working Groups** | Sector working Groups** | Province steering committees
 | District Joint Action Development forum |  | 
Community outreach | Umuganda, focus group discussion, media |  | 

## Slide 13: EDPRS 3 Accomplished Milestones
EDPRS 3 and related Sector and Districts Development Strategies
  Unfinished targets of Vision 2020 identified in NLR – Catchup plan to be part of EDPRS 3
  EDPRS 2 midterm Evaluation underway – Final Report expected in the week of 29th May – 2nd June 2017
  Methodology guidelines for EDPRS 3 elaboration developed & issued to Sectors & Districts
  Initiated procurement of different consultancies that will facilitate the elaboration process including the Communication Firm

## Slide 14: EDPRS 3 Roadmap
Summary Roadmap for Key Deliverables
  Communication campaign for EDPRS 3– to be conducted in June 2017
  Sectors submission of draft priorities, interventions and M&E matrix (including targets for Vision 2050, SDGs, EDPRS 3) – May – June 2017
  1st Draft EDPRS 3- July 2017
  2nd Draft EDPRS 3- August 2017
  Final 7YGP Document- September 2017
  Final document EDPRS 3 - November 2017

## Slide 15: EDPRS 3 Summary Roadmap
Final Drafts EDPRS 3 & Vision 2050
1st Draft EDPRS 3 & Vision 2050
January –September 2017
March to May 2017
June 2017
July 2017
August 2017
November 2017
2nd Draft EDPRS 3 & Vision 2050
Consultations & wider stakeholder engagement
Broad lines presented in NDC 2016
    Continued consultation with different stakeholders + Communication process
Undertake the EDPRS2 Mid- term Evaluation, Trainings & draft priorities for long & medium term
December 2016

## Slide 16
THANK YOU